## Answer Report 1
Microsoft Excel 14.0 Answer Report
Worksheet: [project.xlsx]Software Project
Report Created: 1/19/2015 2:25:42 PM
Result: Solver found a solution. All Constraints and optimality conditions are satisfied.
Solver Engine
Engine: Simplex LP
Solution Time: 0.016 Seconds.
Iterations: 12 Subproblems: 0
Solver Options
Max Time Unlimited, Iterations Unlimited, Precision 0.000001, Use Automatic Scaling
Max Subproblems Unlimited, Max Integer Sols Unlimited, Integer Tolerance 1%, Assume NonNegative
Objective Cell (Min)
| Cell | Name | Original Value | Final Value
| $I$3 | N/A Objective | 25 | 25
Variable Cells
| Cell | Name | Original Value | Final Value | Integer
| $G$3 | N/A Starting Times | 0 | 0 | Contin
| $G$4 | N/A Starting Times | 0 | 0 | Contin
| $G$5 | B Starting Times | 8 | 8 | Contin
| $G$6 | A, C Starting Times | 12 | 12 | Contin
| $G$7 | D Starting Times | 19 | 19 | Contin
| $G$8 | D Starting Times | 21 | 21 | Contin
| $G$9 | D Starting Times | 17 | 17 | Contin
| $G$10 | G Starting Times | 20 | 20 | Contin
| $G$11 | E, F, H Starting Times | 24 | 24 | Contin
| $G$12 | I Starting Times | 25 | 25 | Contin
Constraints
| Cell | Name | Cell Value | Formula | Status | Slack
| $C$15 | B-C LHS | 8 | $C$15>=$D$15 | Not Binding | 5
| $C$16 | A-D LHS | 12 | $C$16>=$D$16 | Binding | 0
| $C$17 | C-D LHS | 4 | $C$17>=$D$17 | Binding | 0
| $C$18 | D-E LHS | 7 | $C$18>=$D$18 | Not Binding | 2
| $C$19 | D-F LHS | 9 | $C$19>=$D$19 | Not Binding | 4
| $C$20 | D-G LHS | 5 | $C$20>=$D$20 | Binding | 0
| $C$21 | G-H LHS | 3 | $C$21>=$D$21 | Binding | 0
| $C$22 | E-I LHS | 5 | $C$22>=$D$22 | Binding | 0
| $C$23 | F-I LHS | 3 | $C$23>=$D$23 | Binding | 0
| $C$24 | H-I LHS | 4 | $C$24>=$D$24 | Binding | 0
| $C$25 | I-Finish LHS | 1 | $C$25>=$D$25 | Binding | 0

## Sensitivity Report 1
Microsoft Excel 14.0 Sensitivity Report
Worksheet: [project.xlsx]Software Project
Report Created: 1/19/2015 2:25:42 PM
Variable Cells
|  |  | Final | Reduced | Objective | Allowable | Allowable
| Cell | Name | Value | Cost | Coefficient | Increase | Decrease
| $G$3 | N/A Starting Times | 0 | 1 | 0 | 1e+30 | 1
| $G$4 | N/A Starting Times | 0 | 0 | 0 | 1e+30 | 0
| $G$5 | B Starting Times | 8 | 0 | 0 | 0 | 1
| $G$6 | A, C Starting Times | 12 | 0 | 0 | 1e+30 | 1
| $G$7 | D Starting Times | 19 | 0 | 0 | 0 | 1
| $G$8 | D Starting Times | 21 | 0 | 0 | 0 | 1
| $G$9 | D Starting Times | 17 | 0 | 0 | 1e+30 | 1
| $G$10 | G Starting Times | 20 | 0 | 0 | 1e+30 | 1
| $G$11 | E, F, H Starting Times | 24 | 0 | 0 | 1e+30 | 1
| $G$12 | I Starting Times | 25 | 0 | 1 | 1e+30 | 1
Constraints
|  |  | Final | Shadow | Constraint | Allowable | Allowable
| Cell | Name | Value | Price | R.H. Side | Increase | Decrease
| $C$15 | B-C LHS | 8 | 0 | 3 | 5 | 1e+30
| $C$16 | A-D LHS | 12 | 1 | 12 | 1e+30 | 5
| $C$17 | C-D LHS | 4 | 0 | 4 | 5 | 1e+30
| $C$18 | D-E LHS | 7 | 0 | 5 | 2 | 1e+30
| $C$19 | D-F LHS | 9 | 0 | 5 | 4 | 1e+30
| $C$20 | D-G LHS | 5 | 1 | 5 | 1e+30 | 2
| $C$21 | G-H LHS | 3 | 1 | 3 | 1e+30 | 2
| $C$22 | E-I LHS | 5 | 0 | 5 | 2 | 1e+30
| $C$23 | F-I LHS | 3 | 0 | 3 | 4 | 1e+30
| $C$24 | H-I LHS | 4 | 1 | 4 | 1e+30 | 2
| $C$25 | I-Finish LHS | 1 | 1 | 1 | 1e+30 | 25

## Software Project
Activity | Description | Predecessor | Time | Starting Times |  | Objective
A | Develop program | N/A | 12 | 0 |  | 25
B | Design usability tests | N/A | 3 | 0
C | Recruit beta testers | B | 4 | 8
D | Test/refine | A, C | 5 | 12
E | Write user’s manual | D | 5 | 19
F | Production | D | 3 | 21
G | Design package artwork | D | 3 | 17
H | Manufacture package | G | 4 | 20
I | Distribute | E, F, H | 1 | 24
Finish | Finish | I | 0 | 25 | (Duration)
Constraints | LHS | RHS
B-C | 8 | 3
A-D | 12 | 12
C-D | 4 | 4
D-E | 7 | 5
D-F | 9 | 5
D-G | 5 | 5
G-H | 3 | 3
E-I | 5 | 5
F-I | 3 | 3
H-I | 4 | 4
I-Finish | 1 | 1